## ERP-Implementation-Phase-Plan-E
ERP Implementation Phase Plan E Commerce
Phase | Duration | Result | E-commerce tasks
1. Goals and processes | 3 to 6 weeks | Target processes, volumes, budget | Map flows per channel, returns, payment and shipping methods
2. Selection | 4 to 10 weeks | System and partner chosen | Check store and marketplace connectors, talk to customers on the same store platform
3. Fit to standard | 3 to 6 weeks | Concept with gaps and solutions | Decide which system owns which data; stock sync timing and buffers
4. Setup and integrations | 6 to 16 weeks | Configured system | Connect store, marketplaces, warehouse, shipping, payments and accounting
5. Data migration | parallel to phase 4 | Clean data, 2 to 3 trial runs | Products, variants, EANs, customers, open orders, stock
6. Testing and training | 3 to 6 weeks | Sign-off by each team | Test order per channel and payment method, return, cancellation, partial delivery
7. Go-live and aftercare | 1 weekend plus 4 to 8 weeks | Stable operations | Plan the cutover, transfer final data, check stock, fix issues fast
Mehr E-Commerce-Insights auf wernerstrauch.de